# Anatomical Heart Digital Twin – 40 Day Task Plan

## Week 1 – Medical Imaging Orientation & Data Readiness

Day 1 – Learn DICOM basics and cardiac MRI anatomy. Deliverable: Screenshot of MRI slices.

Day 2 – Install and explore 3D Slicer. Deliverable: Screenshot of loaded MRI.

Day 3 – Download ACDC dataset and assign patient ID. Deliverable: Folder structure screenshot.

Day 4 – Load patient MRI and identify End-Diastole frame. Deliverable: ED slice screenshot.

Day 5 – Identify LV and myocardium structures. Deliverable: Annotated screenshot.

## Week 2 – Exact Anatomical Segmentation

Day 6 – Start LV cavity segmentation. Deliverable: Partial segmentation screenshot.

Day 7 – Complete LV segmentation. Deliverable: 3D LV preview.

Day 8 – Start myocardium segmentation. Deliverable: Overlay screenshot.

Day 9 – Complete myocardium segmentation. Deliverable: Clean 3D preview.

Day 10 – Segmentation quality validation. Deliverable: Before/after screenshots.

## Week 3 – 3D Geometry Generation

Day 11 – Export 3D models. Deliverable: STL/OBJ files.

Day 12 – Inspect mesh quality. Deliverable: Mesh screenshot.

Day 13 – Clean and smooth mesh. Deliverable: Clean mesh screenshot.

Day 14 – Perform mesh decimation. Deliverable: Triangle stats comparison.

Day 15 – Freeze geometry and archive. Deliverable: Final geometry file.

## Week 4 – Gaussian Splatting Conversion

Day 16 – Convert mesh to point cloud. Deliverable: Point cloud visualization.

Day 17 – Generate Gaussian primitives. Deliverable: Gaussian data file.

Day 18 – Apply color and tissue labeling. Deliverable: Colored Gaussian preview.

Day 19 – Tune Gaussian density. Deliverable: Comparison screenshots.

Day 20 – Validate anatomical fidelity. Deliverable: MRI vs Gaussian comparison.

## Week 5 – Motion & Temporal Twin

Day 21 – Render static twin baseline. Deliverable: Performance metrics.

Day 22 – Introduce contraction motion. Deliverable: Motion preview video.

Day 23 – Apply physiology-driven motion. Deliverable: HR vs motion observation.

Day 24 – Conduct motion stability test. Deliverable: Stability log.

Day 25 – Freeze motion parameters. Deliverable: Motion configuration file.

## Week 6 – Digital Twin Validation

Day 26 – HR sensitivity testing. Deliverable: HR vs motion comparison.

Day 27 – Geometry sensitivity testing. Deliverable: Scale vs shape analysis.

Day 28 – Gaussian performance tuning. Deliverable: FPS comparison results.

Day 29 – Long-run stability test. Deliverable: Stability metrics.

Day 30 – Validation summary. Deliverable: Observational report.

## Week 7 – VR Integration

Day 31 – Setup Unity and Meta Quest. Deliverable: VR environment screenshot.

Day 32 – Static VR heart rendering. Deliverable: VR preview screenshot.

Day 33 – Motion-enabled VR twin. Deliverable: VR motion video.

Day 34 – Add VR interaction controls. Deliverable: Interaction demonstration.

Day 35 – Log VR performance metrics. Deliverable: FPS/latency report.

## Week 8 – Finalization & Documentation

Day 36 – Freeze final digital twin instance. Deliverable: Final twin file.

Day 37 – Repeatability testing. Deliverable: Reproducibility confirmation.

Day 38 – Compile screenshots, videos, and logs. Deliverable: Evidence archive.

Day 39 – Review novelty and IP potential. Deliverable: Innovation notes.

Day 40 – Final demo and presentation. Deliverable: Demo video and summary.